# SCaLE 23x - Show Setup Plan

# Tech Team Mission: Providing the best, open network possible for attendees, speakers, and sponsors.

# Prime Directives for 23x

- WiFi doesn't suck

- Cabling looks good

# Room Layouts for 23x

# https://docs.google.com/spreadsheets/d/1X_xR7MbCXd2M-XjZxDOQSh6LIHLpzBIwpy_qBeCaeQ0/edit?gid=0#gid=0

# Pre Show

- IPv6 Prefix from HE Owen’s: confirmed we are keeping our existing IPv6 prefix (YES)

- Identify all rooms layouts drop dead date for deployment

- Create maps showing desired AP locations in rooms (need to confirm room layouts)

- Pre-ordered wired connections for expo vendors if needed

- Order Rental Truck from Galpin

  - Send PO approval doc to Galpin confirming order: https://docs.google.com/document/d/1kCc42yi-zOmCNWkLq2HKiU2QF9bXHOjaUmcXZGUgDD4/edit?usp=sharing

- Confirm game night location (on-site or off)

- Confirm order and delivery of radios and repeater for Volunteer Staff

- Confirm who orders TVs and where are their locations

- Confirm walkie talkie order

  - Optimal config all deployed on 1 building?

- Complete wire layout plan/map

  - Add 15ft to all AV cable length plan

- TV placement for conference (send to Michael Proctor)

- Order Small tables w/table cloths to cover switches (as needed)

  - Ballroom: B, C, D/E (2x), F, H

  - Conference Room: 101, 105, 106, 107, 207, 208, 209, 211

- Inventory APs in use and facts/ap/apuse.csv

- Inventory RPis in facts/pi/pilist.csv

- Email to tech maillist asking for help at Storage on Monday @ 8am (Steve)

- Confirm wall fixes from PCC (if any)

- Is parking included for volunteers with rooms (check with Ilan) - No parking is not covered

- Add all known tech volunteers to the SCALE registration spreadsheet for volunteer passes

- Add github token to each nixos machine to ensure that github rate limits don’t affect ability to read from github for flake inputs.

# Sunday 3/1

Start Time: 7pm

## Goals:

- Confirm full access to storage (codes and keys)

- Core network hardware available for deployment Monday morning

- Initial setup team account for

## Evening

7:00pm

- Pick up NOC tool box, Routers, and certain switches from storage (IDFs, NOC) (Rob/Owen)

9:00pm

Public Storage closes

# Monday 3/2

Start Time: 10am (7am for Storage)

Encore: 1 team member 12pm-10pm

## Goals:

- NOC has internet access

- All wallports toned and updated in spreadsheet

- NOC setup for tech team

- Deploy Walkie Talkie repeater (Czar)

- APs flashed

- Switches flashed

6:00am

Public Storage Opens

7:00am

- Pickup truck from Galpin in Hollywood (David) Reservation #: 816151

- Pick walkie talkie order from front desk: Fedex Track #: 510907267878  (Rob)

8:00am

- Load carts from storage (David/Steve + 3 volunteers)

  - Chris, Danny, & Jeff (Erik available)

9:00am

- Unload carts at conference center (David/Steve + 3 volunteers)

- Return trailer/truck (David)

10:00am

- Breakfast

12:00pm

- Make contact with conference tech liaison: (Leon as of 2025)

- NOC, AVNOC, IDFs switches flashed with configs (Rob/Owen)

- Move IPv6 Prefix from HE to PCC (Owen)

- Deploy network routers (Rob/Owen)

- Start setting up Core servers (Kyle)

- Setup Massflash station (Rob)

- Deploy walkie talkie repeater on roof

  - Appoint a Walkie Talkie Czar - Duties include keeping track of who rented out walkies, and installation of repeater

  - Fill out walkie talkie tracking paperwork (comes with rental usually)

- Set up Printer & Print cable deploy info (Steve/Steven):

  - MAPS - 2 SETS OF FULL MAP & 1 OF EACH ROOM

  - PICK & PULL LIST

  - VOLUNTEER SIGN UP LIST

  - PATCH LIST

  - INDIVIDUAL BIN INVENTORY SHEETS

- Tone Network jacks, update NETWORK JACK SHEETS

- Flash APs via Massflash (Rob/Kyle)

- Flash Switches (Owen)

- Sign server updates (Kyle)

- Test for PMTU: https://github.com/socallinuxexpo/scale-network/issues/1092

# Tuesday 3/3

Start Time: 9am

Encore: 2 team member 1 9am-7pm, 1 12pm-10pm

## Goals:

- All ports patched in both buildings

- WiFi completely up in Conference building

- Network monitored and operational (Erik)

- Sign and Reg Pis Flashed

- Deploy Meshtastic repeater (Ghriz)

- Deploy Carts to individual locations in buildings

- Deploy bins to each room

- Stretch Goal: Catwalk Switch operational and catwalk drops connected and ready to throw down to show floor

9:00am

- Add AP’s to Room Bins

- Add and Remove Ethernet cables for each room bin  (Pick & Pull List)

  - Build Room 211 workshop bin - Needs:

    - 6 dumb switches

    - Various sizes of ethernet 7ft, 10ft, 15ft that we can provide as well for 50+ attendees.

- Patch data jack ports using “PATCH LIST”

  - CONF IDF (mandatory)

  - BALL C IDF (can move to Wed)

  - BALL F IDF (can move to Wed)

  - CATWALK IDF (can move to Wed)

- Deploy Carts to respective locations

  - Deploy Bins to respective rooms

- Room deployment (Conference Building)

  - Switches up and running

  - Deploy 2 cables to podium (mark with Orange Tape)

  - Deploy 1 cable to AV audio equipment (mark with Green Tape)

  - Deploy cable to camera location (mark with Green Tape)

  - Deploy APs (with cables)

5:00pm

SCaLE AV is planning on moving their stuff from storage to the AV NOC

# Wednesday 3/4

Start Time: 9am

Encore: 1 team member 9am-7pm

## Goals:

- WiFi in Expo Building is completely deployed

- Scale Signs deployed on all TVs

- Registration is completely deployed

- Misc: BYO AV Setups operational

- Stretch Goal: WiFi Survey especially in the common areas (downstairs conf center in particular)

9:00am

- Cable Team Briefing (Steven)

- Cable Wrap Demo (Steven)

- Clearly mark AV Wires (Green tape). Speaker Wires (orange tape)

- Start deploying Expo Building Ballrooms:

  - AP deployment

    - AP distance location

  - AV computer cable

  - AV camera cable

  - AV mixer cabled

  - Speaker network cable

  - Tape down cables across any walkways

12:00pm

SCaLE AV Team to setup equipment for SCaLE

PCC TV delivery

- Deploy sign RPis

- Expo Booth Setup

  - Deploy expo hall switches

    - Deploy expo hall APs

    - Expo hall AP distance location

- Reg Setup

  - Reposition Reg switch

    - Cable Reg AP across from reg switch

  - PI kiosk stations

  - AP distance location

5:00pm

Scale Registration Opens

- Check what is and isn’t up before Thursday

  - Switches completely deploy

  - Wifi everywhere

  - AV needs met

  - Monitoring

  - Registration

  - Signs

- The following conferences have BYO AV setups

  - Ballroom F - Kwaai - Drop for the Speakers VLAN for 3rd party AV - layout supporting 4 person panel, table with person behind it, and three tripods

  - Conf 101, 104 - Planet Nix - Drop for 3rd party AV - Still need to check with organizers on needs

- Cleanup for start of show

  - Move carts

    - CART (5, 4, 6) to expo hall behind curtains

    - CART (2) to conf. Halls downstairs walkway

    - CART (1, 3) in NOC

  - Check for stray bins

# Thursday 3/5

Start Time: 8am

Encore: 1 team member 8am-6pm

Goals:

- WiFi in Expo Hall deployed

  - Drop list (UPDATE): https://docs.google.com/spreadsheets/d/1GlYkokdcrHueHG9UWgzTWvFYAoyrrXt_TLQoXI1CbJs/edit?usp=sharing

- Conference building ready for co-located events

- WiFi Survey especially in all common areas

- Stretch Goal: start prepping for game night (on site)

- Stretch goal: Attend some talks

9:00am

Nix Planet Starts

10:00am

All other of Co-located events start

Conf open (ballrooms and conf upstairs)

- pre-ordered wired connections for vendors deployed

- WiFi Survey especially in the common areas

- Game night setup (ball I/J and game APs)

  - Identify game night connectivity

    - Wall ports for ballrooms I, J

      - APs in ballrooms I, J

      - AP distance location

    - Wall ports in game night area

      - APs along walls

      - AP distance location

      - Find locations for APs in game area, not against wall

- Prep Room 211:

  - Deploy bin and hardware for Room 211

  - Confirm speaker drop in Room 211 is working

2:00pm-5:00pm

- Room 211 - Workshop: Self-hosting a Secure Home Lab Provide support since we provided some hardware

5:00pm

- Cable Monkey Welcome Committee - welcome vendors and ask if they need any ethernet cables

  - Pre-ordered wire drops/connections for vendors deployed

    - AWS has requested (2) drops:

      - One at the rear of Booth 212

      - One at the rear of Booth 216

    - Booth 304 - Flox

    - Booth 100 - AREDN

    - Booth 201- CodeRabbit

6:00pm

- Reconfigure APs for room reconfigurations:

  - Migrate APs in Ballroom A, B, C, G

  - Migrate APs in Conf 103, 107, 211

# Friday 3/6

Start Time: 8am

Encore: 1 team member 8am-6pm

## Goals:

- Expo Hall ready for attendees

- Attend some talks

2:00pm

Expo Hall opens

6:00pm

- Reconfigure APs for room reconfigurations:

  - Migrate APs in Conf 207, 208

# Saturday 3/7

Start Time: 8am

Encore: 1 team member 8am-6pm

### Goals:

- Game night AP & Network deployed

- Truck picked up from rental company

9:00am

12:00pm

- Pickup Truck from Galpin Hollywood (Steven)  Reservation #: 816152

5:00pm

Game Night Starts

# Sunday 3/8

Start Time: 8am

Encore: 1 team member 8am-6pm, 1 team member 10am - 8pm

## Goals:

- No interruptions to speakers during teardown

- Carts and equipment are returned to storage

- Tech Team is able to make Scale Team dinner @ 7pm

- Truck returned to Galpin before midnight

1:00pm

- Confirm time and location of department heads meeting (Rob)

  - Plan early breakdown of this room

- Cable wrap review and competition (steven)

2:00pm

Expo hall is open until 2pm

- EXPO HALL ONLY - Cable teardown for starts promptly at 2pm:

  - Collect all APs

  - Collect all Switches and power cords

  - Collect all downstairs cables

  - Collect all drop cables and Catwalk IDF switch

- 2:30pm Deploy carts around show

2:30pm

- Tear down the room where the chair meeting will occur. (Place everything just outside the door.)

- Tear Down Rooms

  - Registration (may be able to start early afternoon)

    - Same crew for Expo should start on this as soon as they finish

    - Expo or 3 PM whichever is later.

  - Ballrooms/ballhall

    - Ball F

    - Ball C

    - Ball I/J

3:00pm

End of the last session except for the keynote

- Tear Down Rooms

  - Lower conf (100 rooms)

  - Upper conf (200 rooms)

  - Ballrooms

    - Ball A

    - Ball B

    - Ball G

    - Ball H

- Pis, APs get returned to the noc via clear bin, all other wires/power strips, wall warts go into room bins (we need to wait for AV to say they are finished.)

- Carts go by the rooms to pick up bins and switches

- Owen’s wagon is sufficient for this task,

- David has been considering building a small box that could hold several switches on a 2 wheel dolly nicely

- Do we want to have a bin per IDF/MDF for the cables used there to have them handy for next year? We do have that for some IDFs, so we’ll see if it seems useful this year

  - I think a single bin for Expo and one for CF would be sufficient. We can’t generally parallelize the IDF teardowns, so the bin can go in the wagon with the switches.

4:00pm

Keynote ends

- Rob and Owen go to IDFs and restore PCC IDFs/MDFs and pull IDF/MDF switches and routers return to NOC and load onto carts.

- Pack up NOC

- Inventory APs for total accounted for

- Inventory Pis for total accounted for

- Load carts in trailer outside conference building, take to storage

- Tear Down Rooms

  - Ball D/E

  - Ball Room Hallways

- Collect Walkie Talkies (Walkie Czar)

- Remove Walkie Repeater(s)

- Remove Meshtastic Repeater

6:00pm

- Return carts to storage (Steven + 3 volunteers)

7:00pm

- Make SCALE Team Dinner

9:00pm

Public Storage closes

11:30pm

- Return truck to Galpin in Hollywood (Steven)

# POST 23x

- Submit expense reports to expense report software (individuals)

- Schedule post mortem