# SCaLE

Pasedena Convention Center

Objectives per day:

Monday:

- stand up Core, NOC, IDFs

- place kits/packs per ballroom and conference room

- confirm connectivity to IDFs

Tuesday:

- install switches, Pi’s, registration and AP’s

- troubleshoot and resolve connectivity to installed hardware

Wednesday:

- Expo Hall set up

- CTF set up

Thursday:

- troubleshoot connectivity to hardware installed in Expo Hall

- test switches installed for CTF

Friday:

- conference support: break fix

Saturday:

- conference support: break fix

- game night set up

Sunday:

- breakdown

- get approval from Ilan/Lei before breaking down registration

- confirm with AV team that rooms can be dismantled

- return to storage prior to SCaLE staff dinner